## VAPT Backlog (26)
ID | Teams Tracker List ID | Reported By | Reported Date | Application | Iteration | Description | Reproduction Steps | Severity | Proof of Concept | Proposed Mitigation | Escalation Level | Dev Comments | Red Team Comments | CVSS v3.1 Vector | Overall CVSS SCORE | Reference | Phase | Phase Theme | Status | Owner | Priority | Target Release | Start Date | Due Date | PR/Commit | Files Changed | Test Cases | Verification | Verified By | Verified Date | Risk Accepted | Notes
1 | 7 | Abdullah Zafar | 2025-11-19 | 10.1.100.37/ztblais | 1 | Cryptographic Failures | Method: Throughout the application Problem: The application uses HTTP instead of HTTPS, causing all data between the client and server to be transmitted in plaintext. This exposes sensitive information—such as login credentials, session cookies, and personal data—to interception, manipulation, and man-in-the-middle (MITM) attacks. Reproduction Steps: 1) Make a request to the specified host 2) Observe it is using http instead of https and our connection is not secure | High | http.png | Enforce HTTPS for all traffic across the application. Configure automatic redirects from HTTP to HTTPS. Implement HTTP Strict Transport Security (HSTS). Ensure SSL/TLS certificates are valid, trusted, and correctly configured. | 2 |  |  | AV:N/AC:H/PR:L/UI:N/S:C/C:H/I:H/A:H | 8.5 | https://www.cloudflare.com/learning/ssl/why-is-http-not-secure | P4 | Crypto & secrets baseline | Not Started |  | P0
2 | 20 | Abdullah Zafar | 2025-11-24 | 10.1.100.37/ztblais | 1 | Stored Cross-Site Scripting (XSS) | Method: POST /ZTBLAIS/Planning/add_audit_team Problem: The application does not validate, sanitize, or encode user-supplied input in the T_NAME field when creating audit teams. This allows an attacker to inject malicious payloads, which is stored in the backend database and later executed when any user (including administrators) opens the team listing page. This can lead to session hijacking, credential theft, unauthorized actions, or full account compromise. Reproduction Steps: 1) Head over to the specified endpoint and add a new team 2) In the team name, add the XSS payload 3) Save it and notice the application accepts and stores the payload 4) Reload the team listing page, the alert executes, confirming stored XSS on every view of the page | High | xss_1.png xss_2.png | Implement server-side input validation and output encoding/sanitization for all user-controlled fields. Enforce a strict Content Security Policy (CSP) to restrict script execution sources. | 2 |  |  | AV:N/AC:L/PR:L/UI:R/S:U/C:H/I:H/A:H | 8 | https://owasp.org/www-community/attacks/xss | P2 | Input sanitization & encoding (XSS/HTML/CSV) | Not Started |  | P0
3 | 15 | Abdullah Zafar | 2025-11-24 | 10.1.100.37/ztblais | 1 | Rate-Limiting Not Implemented | Method: POST /ZTBLAIS/Login/DoLogin Problem: Rate-limiting is not implemented on the login page. A user can login to his account even after multiple failed attempts. This can lead to attacks like credential stuffing, dictionary, and brute-force. Reproduction Steps: 1) Launch a password brute-force attack on the login page 2) Make sure the payloads are properly encoded before processing (URL and Base64) 3) When it ends, sort the results by length and you'll get the correct password | High | rate_limit_1.png rate_limit_2.png | Implement rate-limiting at the login page and all other endpoints of the application. | 2 |  |  | AV:N/AC:L/PR:N/UI:N/S:U/C:L/I:L/A:L | 7.3 | https://owasp.org/API-Security/editions/2019/en/0xa4-lack-of-resources-and-rate-limiting | P3 | Rate limiting & resource controls | Not Started |  | P0
4 | 17 | Abdullah Zafar | 2025-11-24 | 10.1.100.37/ztblais | 1 | Identification and Authentication Failure | Method: GET /ZTBLAIS/ApiCalls/getallparatext Problem: The web app processes requests even when no session cookie is provided, allowing unauthenticated users to access protected functionalities. This lack of proper session validation exposes the system to unauthorized access. Reproduction Steps: 1) Head over to the specified endpoint 2) Remove the cookie and process the request 3) Observe that it processed successfully | High | iden_1.png iden_2.png | Implement strict session validation on every request to ensure it originates from an authenticated user with a valid session cookie. Enforce authorization checks at the server side before processing any sensitive action. | 2 |  |  | AV:N/AC:L/PR:N/UI:N/S:U/C:L/I:L/A:L | 7.3 | https://owasp.org/Top10/A07_2021-Identification_and_Authentication_Failures | P1 | Auth/session enforcement | Not Started |  | P0
5 | 21 | Sadin Ashraf | 2025-11-24 | 10.1.100.37/ztblais | 1 | HTML Injection Attack | Method: POST /ZTBLAIS/Planning/add_audit_team HTTP/1.1 Problem: HTML injection attacks occur when malicious code is injected into a web page, potentially compromising user data, spreading malware, or redirecting users to harmful websites. Reproduction Steps: 1. Login and go to notice board 2. Add new noticeboard and injection html payload | High | Click_injection_1.png | Ensure that input data are properly escaped, sanitized and HTML encoded. This will ensure that only valid data can be put into the system and that any attempts to write HTML and or JavaScript will properly be rendered as text instead of executing as code. | 2 |  |  | AV:L/AC:L/PR:L/UI:N/S:U/C:H/I:H/A:N | 7.1 |  | P2 | Input sanitization & encoding (XSS/HTML/CSV) | Not Started |  | P0
6 | 23 | Sadin Ashraf | 2025-11-24 | 10.1.100.37/ztblais | 1 | Broken Access Control | Method: POST /ZTBLAIS/HM/SbpObservationRegister HTTP/1.1 Problem: The application provides a password-protected feature after login, but the password field accepts any random value and still grants access. This indicates missing or ineffective server-side authorization validation. Reproduction Steps: 1. Login into application 2. Go to SBP observation register 3. Enter any random password and observe that it process the request successfully | High | improper_checks.png | Implement strict server-side validation for the password and enforce proper authorization checks before granting access to the protected module. Do not rely on client-side checks. Log invalid attempts, enforce rate-limiting, and ensure the password mechanism cannot be bypassed with arbitrary input. | 2 |  |  | AV:L/AC:L/PR:L/UI:N/S:U/C:H/I:H/A:N | 7.1 |  | P1 | Auth/session enforcement | Not Started |  | P0
7 | 25 | Sadin Ashraf | 2025-11-24 | 10.1.100.37/ztblais | 1 | CSV Injection | Method: POST /ZTBLAIS/ApiCalls/add_exception_account_report HTTP/1.1 Problem: CSV injection, also known as formula injection, occurs when untrusted input is embedded into CSV files. This can lead to the execution of malicious scripts if the CSV file is opened in a spreadsheet application like Microsoft Excel or LibreOffice Calc. Reproduction Steps: 1. Login and go to Exception Report 2. Add report and enter payload 3. Download Excel file and observe that payload gets executed | High | CSV_Injection_2.png CSV_Injection_1.png | Implement validation and sanitization at the point of data entry to prevent malicious inputs from being saved in the first place. | 2 |  |  | AV:L/AC:L/PR:L/UI:N/S:U/C:H/I:H/A:N | 7.1 |  | P2 | Input sanitization & encoding (XSS/HTML/CSV) | Not Started |  | P0
8 | 14 | Sadin Ashraf | 2025-11-21 | 10.1.100.37/ztblais | 1 | Identification and Authentication Failure | Method: Throughout the site Problem: The web application processes requests even when no session cookie is provided, allowing unauthenticated users to access protected functionality. This lack of proper session validation exposes the system to unauthorized access. As a result, sensitive operations can be performed without verifying the user’s identity. Reproduction Steps: 1. Login into application and go to the mentioned endpoint 2. Remove the cookie and process the request 3. Observe that it processed successfully | High | session_failures_3.png session_failures_5.png session_failures_4.png session_failures_2.png session_failures_6.png session_failures_1.png | Implement strict session validation on every request to ensure it originates from an authenticated user with a valid session cookie. Enforce authorization checks at the server side before processing any sensitive action. | 2 |  |  | AV:L/AC:L/PR:L/UI:N/S:U/C:H/I:N/A:H | 7.1 |  | P1 | Auth/session enforcement | Not Started |  | P0
9 | 10 | Sadin Ashraf | 2025-11-20 | 10.1.100.37/ztblais | 1 | Broken Access Control (Improper Session Management) | Method: Problem: The application fails to properly terminate an existing user session when a new login occurs, allowing the previous session to remain partially active. As a result, the user who should have been logged out can still perform actions by directly interacting with backend, creating a security risk. Reproduction Steps: 1. Login into an account and keep the session open 2. Login into same account from another location and use kill session option to kill existing session 3. Return to 1st session and observe that it is still partially logged in and allows user to use sensitive functionality like changing password | High | session_management_3.png session_management_2.png session_management_1.png session_management_4.png | Implement proper session invalidation by fully destroying the existing session token when someone kill session, ensuring no further actions can be performed from the old session. | 2 |  |  | AV:L/AC:L/PR:L/UI:N/S:U/C:H/I:N/A:H | 7.1 |  | P1 | Auth/session enforcement | Not Started |  | P0
10 | 16 | Abdullah Zafar | 2025-11-24 | 10.1.100.37/ztblais | 1 | Cryptographic Failures | Method: POST /ZTBLAIS/Login/DoLogin Problem: The User id and userEntityID are not encrypted and exposed in the response Reproduction Steps: 1) Make a request to the specified endpoint and login 2) Notice the exposed sensitive details | Medium | crypto_1.png | Remove or properly encrypt all sensitive IDs, email addresses, and other details. | 2 |  |  | AV:N/AC:L/PR:L/UI:N/S:U/C:H/I:N/A:N | 6.5 | https://owasp.org/Top10/A02_2021-Cryptographic_Failures | P4 | Crypto & secrets baseline | Not Started |  | P1
11 | 5 | Abdullah Zafar | 2025-11-18 | 10.1.100.37/ztblais | 1 | Content Security Policy Not Implemented | Method: Throughout the application Problem: It was detected that the web app lacks the Content Security Policy (CSP) as it is not implemented throughout the site. CSP is an added layer of security that helps to detect and mitigate certain types of attacks, including Cross Site Scripting (XSS) and data injection attacks. Reproduction Steps: 1) Login to the web app and go to the home page (or any page) 2) Capture the response and insert a payload in the body 3) Forward the request and notice the alert pops up 4) Additionally, note that the web app lacks CSP in response headers | Medium | csp_1.png csp_2.png csp_3.png | It is recommended to implement CSP into the web app and enforce it thoroughly. | 2 |  |  | AV:N/AC:L/PR:L/UI:N/S:U/C:H/I:N/A:N | 6.5 | https://developer.mozilla.org/en-US/docs/Web/HTTP/CSP | P5 | Security headers & browser hardening | Not Started |  | P1
12 | 4 | Sadin Ashraf | 2025-11-18 | 10.1.100.37/ztblais | 1 | Insecure Design (Weak Password Policy) | Method: POST /ZTBLAIS/Home/DoChangePassword HTTP/1.1 Problem: Password policy is implemented on Client's end (WebApp). Users can register with weak passwords by directly interacting with backend service. Reproduction Steps: 1. Login and go to password change interface 2. Change password, intercept request the DoChangeRequest using any proxy and change the password again 3. Observe that it changes password to any string, ignoring the Client site restrictions | Medium | Password_policy_2.png Password_policy.png | Implement strong password policy at server side. | 2 |  |  | AV:L/AC:L/PR:L/UI:N/S:U/C:H/I:N/A:N | 5.5 |  | P6 | Account protection (password/MFA/CAPTCHA) | Not Started |  | P1
13 | 19 | Abdullah Zafar | 2025-11-24 | 10.1.100.37/ztblais | 1 | Insecure Direct Object Reference (IDOR) | Method: GET /ZTBLAIS/ApiCalls/getallparatext Problem: The endpoint returns data based solely on a numeric comId supplied in the URL. Changing its values returns different data. Since the endpoint accepts unauthenticated requests, an attacker can enumerate IDs at scale and retrieve arbitrary values. This lack of object-level authorization is a classic IDOR. Reproduction Steps: 1) Head over to the specified endpoint 2) Change values of comId in the URL and notice different data returned | Medium | idor_1.png idor_2.png idor_3.png | Avoid direct sequential numeric IDs in URLs (use opaque/unguessable IDs or signed/hashed identifiers); require authentication for all endpoints' access; add logging, rate-limiting and monitoring for unusual enumeration patterns. | 2 |  |  | AV:N/AC:L/PR:N/UI:N/S:U/C:L/I:N/A:N | 5.3 | https://portswigger.net/web-security/access-control/idor | P1 | Auth/session enforcement | Not Started |  | P1
14 | 26 | Abdullah Zafar | 2025-11-24 | 10.1.100.37/ztblais | 1 | Unrestricted Resource Consumption | Method: POST /ZTBLAIS/ApiCalls/add_audit_sub_checklist Problem: The specified endpoint allows unrestricted Checklist addition, enabling attackers to brute-force and create an unlimited number of checklists. This can lead to resource exhaustion, database bloat, and potential abuse of the system. Reproduction Steps: 1) Send a valid request to the specified endpoint to create a checklist 2) Brute-force the endpoint by iterating through different fields 3) Observe that the server allows unlimited number of checklist registration without any rate limiting or restrictions | Medium | brute_1.png brute_2.png | Implement rate limiting on all such fields and endpoints to restrict the number of requests from a single IP address within a specific timeframe. Additionally, incorporate CAPTCHA verification to prevent automated requests | 2 |  |  | AV:N/AC:L/PR:N/UI:N/S:U/C:L/I:N/A:N | 5.3 | https://owasp.org/www-community/attacks/Brute_force_attack | P3 | Rate limiting & resource controls | Not Started |  | P1
15 | 11 | Sadin Ashraf | 2025-11-20 | 10.1.100.37/ztblais | 1 | Username Enumeration | Method: POST /ZTBLAIS/Login/KillSession HTTP/1.1 Problem: It is possible to distinguish between valid and invalid PPNumber/CNIC based on response content. The response for a fake user shows the message incorrect and shows nothing on the user interface while the response for a real user shows the message success as well as a message. Attacker may used brute forcing technique to list down all valid PPNumber/CNIC. Reproduction Steps: 1. Open webapp and go to forgot password interface 2. Enter valid and invalid parameters and observe response | Medium | username_enum_2.png username_enum_1.png username_enum_3.png | The response for valid and invalid user should be the same like "if PPNumber/CNIC existed in our database, password reset link will be sent on email" so that the attacker cant distinguish between valid and invalid users. | 2 |  |  | AV:L/AC:H/PR:L/UI:N/S:U/C:H/I:N/A:N | 4.7 |  | P6 | Account protection (password/MFA/CAPTCHA) | Not Started |  | P1
16 | 9 | Abdullah Zafar | 2025-11-19 | 10.1.100.37/ztblais | 1 | Insecure Design (MFA and CAPTCHA Not Implemented) | Method: Login Page Problem: Multi-factor authentication and CAPTCHA control not implemented on the login page. Raises the risk of identification and authentication failure vulnerabilities. Reproduction Steps: 1) Go to login page 2) Only password authentication is there, no MFA or CAPTCHA | Medium | login_1.png login_2.png | Implement multi-factor authentication and CAPTCHA control on the login page, specially for admin users. | 2 |  |  | AV:N/AC:L/PR:N/UI:R/S:U/C:L/I:N/A:N | 4.3 | https://docs.fluidattacks.com/criteria/vulnerabilities/081 | P6 | Account protection (password/MFA/CAPTCHA) | Not Started |  | P1
17 | 24 | Sadin Ashraf | 2025-11-24 | 10.1.100.37/ztblais | 1 | Security Misconfiguration (Verbose Error) | Method: POST /ZTBLAIS/FAD/StaffPositionCreate HTTP/1.1 Problem: Verbose error page is being shown. The application exposes full stack traces and internal system details when an error occurs, revealing file paths, source code structure, and server information. This information disclosure increases the risk of targeted attacks and compromises the security posture of the system. Reproduction Steps: 1. Login as Admin 2. Add Staff Position and Observe it shows verbose error | Medium | verbose_error_1.png | Properly hide or remove sensitive information. Use generic error message in case of error. | 2 |  |  | AV:L/AC:L/PR:N/UI:N/S:U/C:L/I:N/A:N | 4 |  | P5 | Security headers & browser hardening | Not Started |  | P1
18 | 12 | Sadin Ashraf | 2025-11-20 | 10.1.100.37/ztblais | 1 | Security Misconfiguration (Verbose Error) | Method: Throughout the site Problem: Verbose error page is being shown. The application exposes full stack traces and internal system details when an error occurs, revealing file paths, source code structure, and server information. This information disclosure increases the risk of targeted attacks and compromises the security posture of the system. Reproduction Steps: 1. Open webapp 2. Enter invalid parameter to cause application to release verbose error page | Medium | verbose_error.png | Properly hide or remove sensitive information. Use generic error message in case of error. | 2 |  |  | AV:L/AC:L/PR:N/UI:N/S:U/C:L/I:N/A:N | 4 |  | P5 | Security headers & browser hardening | Not Started |  | P1
19 | 18 | Abdullah Zafar | 2025-11-24 | 10.1.100.37/ztblais | 1 | Cryptographic Failures | Method: GET /ZTBLAIS/ApiCalls/getallparatext Problem: The comId is not encrypted, exposed, and passing directly in the URL. Reproduction Steps: 1) Make a request to the specified endpoint 2) Notice the unencrypted comId passing through the URL | Low | crypto_2.png | Encrypt or obfuscate sensitive details and make sure they are not included in the URL. | 2 |  |  | AV:N/AC:H/PR:N/UI:N/S:U/C:L/I:N/A:N | 3.7 | https://owasp.org/Top10/A02_2021-Cryptographic_Failures | P4 | Crypto & secrets baseline | Not Started |  | P2
20 | 22 | Abdullah Zafar | 2025-11-24 | 10.1.100.37/ztblais | 1 | Outdated jQuery Library | Method: GET /ztblais/lib/jquery/dist/jquery.min.js Problem: The application is serving an outdated jQuery library (3.5.1). Using an outdated version increases the risk of client-side compromise and supply-chain exposure. Reproduction Steps: 1) Head over to the specified endpoint 2) Observe the use of jQuery 3.5.1 | Low | vuln_3.png | Upgrade jQuery to the latest stable release (3.7.1) and disable support for older versions. | 2 |  |  | AV:N/AC:H/PR:N/UI:N/S:U/C:L/I:N/A:N | 3.7 | https://jquery.com/download | P5 | Security headers & browser hardening | Not Started |  | P2
21 | 13 | Abdullah Zafar | 2025-11-21 | 10.1.100.37/ztblais | 1 | TRACE Method Enabled | Method: Throughout the application Problem: The server supports the HTTP TRACE method, enabling Cross-Site Tracing (XST) attacks that could allow attackers to steal sensitive data, such as session cookies, by exploiting client-side vulnerabilities, potentially leading to session hijacking or unauthorized access. Reproduction Steps: 1) Verify the use of TRACE method | Low | trace_1.png trace_2.png | Disable the TRACE method in Microsoft IIS/10.0 by adding <verbs><add verb="TRACE" allowed="false" /></verbs> to the web.config file under <system.webServer><security><requestFiltering>, or use IIS Manager to deny TRACE in the "Request Filtering" HTTP Verbs tab. Verify the change with OPTIONS/TRACE requests and consider deploying a Web Application Firewall (WAF) to block TRACE requests for additional protection. | 2 |  |  | AV:N/AC:H/PR:N/UI:N/S:U/C:L/I:N/A:N | 3.7 | https://abineshm.medium.com/http-trace-method-vulnerability-and-fixing-84355335c338 | P5 | Security headers & browser hardening | Not Started |  | P2
22 | 8 | Abdullah Zafar | 2025-11-19 | 10.1.100.37/ztblais | 1 | Clickjacking: X-Frame-Options Header | Method: Throughout the application Problem: Absence of X-Frame-Options header leaves the site vulnerable to clickjacking attacks, potentially risking unauthorized actions and data exposure during user interactions Reproduction Steps: 1) Verify lack of anti-clickjacking header by running a Nikto scan on the target host 2) Also, capture any request of the specified host and notice that the response headers lack X-Frame-Options header | Low | click_1.png click_2.png | Configure the server to include an X-Frame-Options header and a CSP header with frame-ancestors directive all across the web app. | 2 |  |  | AV:N/AC:H/PR:N/UI:N/S:U/C:L/I:N/A:N | 3.7 | https://www.acunetix.com/vulnerabilities/web/clickjacking-x-frame-options-header | P5 | Security headers & browser hardening | Not Started |  | P2
23 | 2 | Abdullah Zafar | 2025-11-18 | 10.1.100.37/ztblais | 1 | Vulnerable and Outdated Components | Method: GET /.aspx Problem: The application is using X-AspNet-Version: 4.0.30319, which is outdated and have many CVEs which make the framework vulnerable. Reproduction Steps: 1) Make a request to the specified endpoint 2) Notice the vulnerable AspNet Version | Low | vuln_1.png vuln_2.png | Update ASP to latest version and disable support for the older version. Additionally, disable version disclosure headers by configuring the application to hide framework details. | 2 |  |  | AV:N/AC:H/PR:N/UI:N/S:U/C:L/I:N/A:N | 3.7 | https://stackoverflow.com/questions/74890132/clr-4-0-30319-vulnerabilities | P5 | Security headers & browser hardening | Not Started |  | P2
24 | 3 | Abdullah Zafar | 2025-11-18 | 10.1.100.37/ztblais | 1 | Security Misconfiguration | Method: Throughout the application Problem: The server exposes the underlying HTTP.sys component through the "Server: Microsoft-HTTPAPI/2.0" header when handling malformed requests. Reproduction Steps: 1) Make a malformed request to the specified host and observe "Microsoft-HTTPAPI/2.0" exposed in the response | Low | server.png | Sensitive information should be removed or hidden properly. | 2 |  |  | AV:N/AC:H/PR:N/UI:N/S:U/C:L/I:N/A:N | 3.7 | https://owasp.org/Top10/A05_2021-Security_Misconfiguration | P5 | Security headers & browser hardening | Not Started |  | P2
25 | 6 | Abdullah Zafar | 2025-11-19 | 10.1.100.37/ztblais | 1 | Cookies Without Secure Flag Set | Method: Throughout the application Problem: Cookies don't have the Secure flag set. This can allow the cookies to be accessed over insecure SSL/TLS channels. Reproduction Steps: 1) Right-click on the web app and open 'Inspect Element' 2) Navigate to 'Storage -> Cookies' 3) Notice that the Secure flag for cookies is set to false | Low | secure.png | Set the Secure flag for cookies. | 2 |  |  | AV:N/AC:L/PR:L/UI:R/S:U/C:N/I:L/A:N | 3.5 | https://www.zaproxy.org/docs/alerts/10011 | P5 | Security headers & browser hardening | Not Started |  | P2
26 | 1 | Sadin Ashraf | 2025-11-18 | 10.1.100.37/ztblais | 1 | Security Misconfigurations | Method: Throughout the site Problem: The application is exposing two server-related headers in its HTTP responses: “Server: Microsoft-IIS/10.0” and “X-Powered-By: ASP.NET.” These headers reveal the exact web server (IIS 10.0) and backend framework (ASP.NET) used by the application. Disclosing this information is unnecessary and increases security risk because attackers can use these details to identify known vulnerabilities and launch targeted attacks. | Low | header_disclose.png | Remove or suppress the Server and X-Powered-By headers from HTTP responses to avoid disclosing server and framework details. This can be done via IIS configuration (web.config) or using HTTP header filtering modules. Regularly review server headers to ensure no sensitive information is exposed. | 2 |  |  | AV:L/AC:H/PR:N/UI:N/S:U/C:L/I:N/A:N | 2.9 | https://learn.microsoft.com/en-au/answers/questions/2182820/how-to-hide-server-and-x-powered-by-response-heade?utm_source=chatgpt.com | P5 | Security headers & browser hardening | Not Started |  | P2

## Phases
Phase | Phase Theme | Items | High | Medium | Low
P1 | Auth/session enforcement | 5 | 4 | 1 | 0
P2 | Input sanitization & encoding (XSS/HTML/CSV) | 3 | 3 | 0 | 0
P3 | Rate limiting & resource controls | 2 | 1 | 1 | 0
P4 | Crypto & secrets baseline | 3 | 1 | 1 | 1
P5 | Security headers & browser hardening | 10 | 0 | 3 | 7
P6 | Account protection (password/MFA/CAPTCHA) | 3 | 0 | 3 | 0
Phase | Theme | Scope / Acceptance Criteria
P1 | Auth/session enforcement | Fix unauthenticated access, session validation, controller permission normalization, stable API auth/403/401 behavior.
P2 | Input sanitization & encoding (XSS/HTML/CSV) | Block < > globally, encode output, sanitize stored content, protect HTML rendering paths, mitigate CSV formula injection.
P3 | Rate limiting & resource controls | Per-user/IP rate limits for sensitive endpoints + request size/timeouts + pagination/limits.
P4 | Crypto & secrets baseline | Strong TLS, remove weak crypto, secure hashing, protect secrets/keys, disable HTTP.
P5 | Security headers & browser hardening | CSP, XFO, HSTS, secure cookie flags, remove TRACE, update vulnerable libs/components, reduce verbose errors.
P6 | Account protection (password/MFA/CAPTCHA) | Password policy, lockout, MFA/CAPTCHA where needed, prevent username enumeration.

## How to use
How to use this tracker
1) Status values: Not Started / In Progress / Done / Blocked / Risk Accepted
2) Owner: person/team responsible (e.g., ISAD, Dev, DBA).
3) PR/Commit: paste Git commit hash or PR link text.
4) Files Changed: list key files only (paths).
5) Test Cases: list the exact test(s) you ran and the result.
6) Verification: 'Dev tested', 'QA tested', 'Red-team retest', etc.
7) Verified By/Date: fill when closed.
Start Now (per your request):
- ID 2 Stored XSS and ID 5 HTML Injection are set to 'In Progress'.